## Slide 1: Project Logic Model Template
Project Objective: e.g. ‘To build effective and safe bystander behaviours amongst participants’.
  External factors: List here factors outside your control that might impact the success of the project (e.g. a reduction in funding, the pandemic, etc.)
  Assumptions: An assumption is any condition that is necessary to make the outcomes in your project successful e.g. a well-trained workshop facilitator if workshops are an output. Outcome definitions have been adapted from State Government of Victoria (2021) Outcomes Reform in Victoria.
This is a template. Please feel free to delete the examples provided and add your own text.
Partners
  (for example community organisations, businesses).
Strategies and Frameworks
Funding
Project Governance
  (for example Steering Group, Advisory Group).
Staff
  (for example project staff, cultural advisors, etc).
Inputs
  (The resources you will use to deliver activities and outputs in the project.)
Activities
  (Project actions that will lead to your outputs.)
Outputs
  (What is produced and delivered.)
Short-term outcomes
  (These are changes you want to see in the short-term – which might be anywhere up to 1 year or so.)
Medium-term outcomes
  (These are changes you want to see in the medium-term – which might be anywhere from 2 to 5 years.)
Long-term outcomes
  (These are changes you want to see in the long-term – which might be anywhere from 5 years onwards.)
Activity 1
  Delivery of ‘Bystander behaviour’ training.
Activity 2
  (Please describe.)
    Copy/paste box to add more activities.
Number and type of activities completed
  (e.g. three bystander training sessions).
Number of participants trained
  (e.g. 20 community members trained per session = 60 participants).
  Relationships formed with key stakeholders.
    Copy/paste box to add more outputs.
  Participants recognise what inappropriate sexist or harassing behaviour looks like. (Example only.)
  Participants learn techniques for assessing when and how to intervene. (Example only.)
    Copy/paste box to add more outcomes.
  Community members make assessments of when and how it is appropriate to intervene. (Example only.)
  Community members have the confidence to intervene. (Example only.)
  Community members begin practising bystander behaviour when small opportunities present. (Example only.)
    Copy/paste box to add more outcomes.
  FFV Outcome – All Victorians live and practice confident and respectful relationships. (Example only.)
    Note – you might also include this as a bigger picture ‘vision’ that sits across the whole diagram.
  Bystander behaviour is a normal part of community action. (Example only.)
For any questions, contact research@respectvictoria.vic.gov.au

## Slide 2: Guidance Notes
  This template can be adapted to better suit your project’s method, cohort or setting.
  The boxes contain examples only. You can fill in boxes based on your own project and add more boxes where needed. The template can be adapted, so long as the logic is clearly displayed.
  Lines can be drawn with arrows in the direction from activities to outputs to outcomes, to show which activities link to which outputs and outcomes. Lines can also be simplified as needed (as shown in input to activities).
  Setting short and medium-term outcomes may depend on the length of your project. If you do set medium-term outcomes, ensure there is a causal pathway from short-term to medium-term outcomes, and then from medium to long-term outcomes.
  Achieving long-term outcomes can take many years. Please select the level of outcomes that are relevant to your project or funding program.
  It is important to discuss external factors and assumptions for your model with your practice group. Where you have the space and time, please include these in the diagram – however, they are not compulsory.
  A logic model helps you track your progress. External considerations and assumptions help you track that progress in context.
  For more guidance on developing a logic model go to the Respect Victoria Monitoring, Evaluation and Learning (MEL) Toolkit website.
For any questions, contact research@respectvictoria.vic.gov.au